## Sheet1
Page | Link | Problem | Comment | Status
Update Profile | http://159.203.77.110/litagram/dashboard/profile | Full Name Field Update - Format wrong | Not able to update name as "Selva". Only "Selva X" is allowed. | Done
Update Profile | http://159.203.77.110/litagram/dashboard/profile | Profile Image Update Not working |  | Done
Update Profile | http://159.203.77.110/litagram/dashboard/profile | Change Password | Placeholder text - change | Done
My Projects | http://159.203.77.110/litagram/dashboard/myprojects | Remove Order Author Copies |  | Done
My Projects | http://159.203.77.110/litagram/dashboard/myprojects | Rename "Edit" to "Continue Publishing" |  | Done - What happens when user clicks on Continue Publishing?
Header |  | Logo to go Dashboard |  | Done
Header |  | Remove Search,Messages, Settings Icons |  | Done
General |  | Bank Account details for each account/book | Where is it? | Done
New Book | http://159.203.77.110/litagram/workflow/booktitle/new | Subtitle | Placeholder text - change | Done
New Book | http://159.203.77.110/litagram/workflow/booktitle/new
New Book | http://159.203.77.110/litagram/workflow/booktitle/new | Series Title | Placeholder text - change | Done
| http://159.203.77.110/litagram/workflow/booktitle/new | Save button notworking |  | Done
| http://159.203.77.110/litagram/workflow/booktitle/new | On save & & Save & Continue | Cover Flag is also set as done | Done
Template | http://159.203.77.110/litagram/workflow/booktemplate/43 | view Sample | Opens blank | Need to figure out on what has to be done after clicking
Template | http://159.203.77.110/litagram/workflow/booktemplate/43 | Most popular trim sizes | Why for the first time also we're getting popup to warn changes. | Done
BookInterior | http://159.203.77.110/litagram/workflow/bookinterior/43 | Write online | Launch online button | Needs Designing
Writing Platform | http://159.203.77.110/litagram/writingplatform/block/43 | Chapters not saving |  | Done
Select Template | http://159.203.77.110/litagram/index.php/writingplatform/templatestyle/43# | Set up templates |  | Need to figure out on what has to be done after clicking
Previewer | http://159.203.77.110/litagram/openPDFReviewer | Previewer opens up only old junior writer orator |  | Done
Cover | http://159.203.77.110/litagram/workflow/cover/43 | View Sample |  | Need to figure out on what has to be done after clicking
Cover | http://159.203.77.110/litagram/workflow/cover/43 | Blue ? |  | Please Elaborate..dint get it
Cover | http://159.203.77.110/litagram/workflow/cover/43 | Sarts to "Starts" |  | Done
Cover Upload | http://159.203.77.110/litagram/workflow/cover/43 | Allow only pdf | Auto remove the file | The Option is not available in Dropzone. Have to figure out something else. Is this mandatory?